## Sheet1
Annotated Milestones
Organization: | CHI St. Vincent Addiction Recovery
Project Title: | 2 Peer Support Positions
Quarter: | All Quarters
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
Hire two peer specialists | Prior to September 1, 2023 3 months after 3 months after funding | X | Hired Jenny Wiens, she started on 9/2/2023. Hourly rate of 16.16/hour. Phil Burr was transferred to this cost center on 9/1/2023.
Develop Peer Support program | Prior to September 1, 2023 3 months after 3 months after funding | X | Program was in place prior to peers starting.
Develop data tracking system Prior to September 1, 2023 3 months after | Prior to September 1, 2023 3 months after 3 months after funding |  | Used info ADP for time and attendance. Discussing how to track transportation and expenses.
Submit first ARORP report | Prior to September 1, 2023 3 months after 3 months after funding |  | Did not have access to the information to report.
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on Peer Support Program Prior to December 1, 2023 6 months after | Prior to December 1, 2023 6 months after funding |  | We have utlized both our peers to work in the community, provide transpotation from treatment to sober living as well as work with the patietns daily in our program. The response has been positive.
Submit Quarterly ARORP report December 1, 2023 6 months after | Decemer 1, 2023 |  | Did not hav eaccess to the information to report.
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on Peer Support Program Prior to December 1, 2023 6 months after | Prior to March , 2024 9 months after funding |  | We only have one peers still under grant funding. The other position was requested numerous occassions throug internal process and was denied due to the census on the unit each week.
Submit Quarterly ARORP report December 1, 2023 6 months after | 2024-03-01 |  | Submitting on 4/19/2024 as program closes.
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
NA | 2024-06-01 |  | Program closed 4/19/24, so the project did not reach quarter 4.