## Sheet1
Life In Victory Recovery Center
Camp Powder Fork 160
Year 1 Annual Milestones
Quarter 1 Milestones | Status | Updates/Notes
Purchased Property | Complete | Purchased Camp Powderfork at 200 Powderfork Rd.
Complete Remodel | Complete | Replaced shingles on 4 cabins and 3 beds house, and built the laundry building. Metal roof 10/6/23, roof on cabins 11/3/23, laundry mat 12/14/23
Developed data tracking system | Complete
Submit first quarterly ARORP report | Complete
Quarter 2 milestones
Hire Director | Complete | Clint Davidson started 10/15/23 with a salary of $30,000.00. Travis Strickland replaced Clint Davidson with a salary of 30,000 on 2/5/24.
Hire Assistant Director | Complete | Jake Neal started 10/15/23 with a salary of $30.000/00. Daniel Schmidt replaced Clint Davidson with a salary of 30,000 on 2/5/24.
Hire Mechanic | Complete | James Everidge started 10/15/23 with a salary of $20,800.00. Codie Teddy replaced James Everidge with a salary of 20,800 on 2/26/24.
Hire Security night guard | Complete | Daniel Schmidt started 10/22/23 with a salary of $20,000.00. Shawn Moore replaced Daniel Schmidt with a salary of 20,800 on 2/5/24. Brandon Norman replaced Shawn moore with a salary of 20,800 on 4/29/24 . Lisa Lauderdale replaced Brandon Norman on 6/14/24.
Hire Peer Specialist | Complete | Lisa Garner started 10/30/23 with a salary of $28,000.00. Rose Shelton was hired as a second peer specialist with a salary of 28,000 on 3/22/24. Angela Heath replaced Rose Shelton on 7/29/24 as peer specialist with a salary of $29,900 yr.
Hire Secretary | Complete | Connie Wilkinson started 11/07/23 with a salary of $24,960.00.
Arorp report | Complete | 2023-12-31
Quarter 3 Milestones
Operate at full capacity for year 1 | Complete | Served at least 102 men (42 original beds, 60 additional ARORP-funded beds)
Arorp Report | Complete
Quarter 4 Milestones
Operate at full capacity | Complete | Served at least 102 men (42 original beds, 60 additional ARORP- funded beds).
Submit annual ARORP report | Complete